## Sheet1
ID | Name | Status | Due | Created | Updated
INRT-827 | API - Bishal - Fix old production bugs | 1. Planned | 2024-02-01 00:00:00 | 2024-01-25 15:32:56 | 2024-01-25 15:34:46
INRT-789 | Maintain old open bugs | 1. Planned | 2024-01-31 00:00:00 | 2023-12-12 11:13:03 | 2024-01-25 15:33:46
INRT-832 | API - We wanted to new incident created on column in the incidents table. Currently we are storing C | 1. Planned | 2024-01-31 00:00:00 | 2024-01-29 09:53:31 | 2024-01-29 09:55:22
INRT-632 | Testing: Raise incident daily to test Notifications & Escalcations | 5. Testing | 2024-01-26 00:00:00 | 2023-08-07 19:37:58 | 2024-01-26 09:12:44
INRT-410 | API - Need to export incident in the OSHA RK Excel - i.e an editable Excel filling available inciden | 3. In review | 2024-01-24 00:00:00 | 2023-03-27 10:37:01 | 2024-01-29 09:15:54
INRT-727 | API - Handle attachments securely | 3. In review | 2024-01-24 00:00:00 | 2023-10-03 18:17:07 | 2024-01-25 11:00:02
INRT-802 | API - Remove user emails, phonenumber in all the log info/error/debug messages (in all the component | 3. In review | 2024-01-24 00:00:00 | 2023-12-20 16:39:08 | 2024-01-29 09:14:56
INRT-153 | [API]: Drop the table incident_fieldstaff | 3. In review | 2024-01-12 00:00:00 | 2022-10-03 13:25:18 | 2023-12-28 18:10:37
INRT-266 | API - hotfix - Upgrade DOTNET version & fix compilation errors if any | 3. In review | 2024-01-12 00:00:00 | 2023-01-09 11:30:46 | 2023-12-28 18:13:26
INRT-330 | App - Push notification/ Whatsapp - On click redirect to incident details page for all incident rel | 2. Development /In Progress | 2024-01-12 00:00:00 | 2023-02-03 19:16:26 | 2024-01-21 19:26:32
INRT-370 | Portal - Incidents - View/Edit incident - Give an option to export OSHA report | 2. Development /In Progress | 2024-01-12 00:00:00 | 2023-02-27 11:12:46 | 2024-01-21 19:28:01
INRT-379 | Portal - Asset - View/Edit asset - Show QR code of that asset and give a print option | 1. Planned | 2024-01-12 00:00:00 | 2023-03-07 14:08:51 | 2024-01-28 12:48:01
INRT-666 | API - Delete User Device - Create new API to delete user device end from Amazon SNS & DB table | 5. Testing | 2024-01-12 00:00:00 | 2023-08-18 20:23:45 | 2024-01-25 15:27:37
INRT-719 | Tech Support - Production exceptions debugging & fixing | 1. Planned | 2024-01-12 00:00:00 | 2023-09-25 16:15:03 | 2024-01-28 23:29:11
INRT-728 | API - Graphs - Monthly report on resolution Time - Create an API to export the attached graph in CSV | 5. Testing | 2024-01-12 00:00:00 | 2023-10-03 18:23:13 | 2023-12-28 18:13:37
INRT-729 | API - Graphs - Overall report on resolution time - Create an API to export the attached graph in CSV | 5. Testing | 2024-01-12 00:00:00 | 2023-10-03 18:24:03 | 2023-12-28 18:19:01
INRT-730 | API - Renewal Reminder - Send an weekly email attaching Overall report on resolution time CSV file & | 3. In review | 2024-01-12 00:00:00 | 2023-10-03 18:25:08 | 2024-01-17 09:58:01
INRT-731 | API - Graphs - Asset types | 6. Ready to go live | 2024-01-12 00:00:00 | 2023-10-03 18:25:41 | 2024-01-24 18:19:47
INRT-732 | API - Graphs - Fieldstaff competency graphs | 6. Ready to go live | 2024-01-12 00:00:00 | 2023-10-03 18:26:06 | 2024-01-24 18:23:10
INRT-734 | API - Create stats graphs | 5. Testing | 2024-01-12 00:00:00 | 2023-10-04 16:37:51 | 2023-12-28 18:20:30
INRT-736 | App - Setup linting and fix the issues, then setup CI | 5. Testing | 2024-01-12 00:00:00 | 2023-10-05 18:46:16 | 2024-01-22 01:44:52
INRT-749 | API - Instead of blank labels in the incident PDF , we can add NA | 4. Integration ready | 2024-01-12 00:00:00 | 2023-10-19 13:55:39 | 2023-12-28 18:16:40
INRT-754 | App - Make sidebar navigation into thumbnails | 5. Testing | 2024-01-12 00:00:00 | 2023-10-25 16:03:40 | 2024-01-29 10:01:18
INRT-756 | App - Call delete device end point API on logout | 5. Testing | 2024-01-12 00:00:00 | 2023-10-30 11:56:02 | 2023-12-28 18:20:40
INRT-757 | Portal - Reports - Graphs by asset ID | 6. Ready to go live | 2024-01-12 00:00:00 | 2023-10-31 11:13:06 | 2024-01-23 12:10:57
INRT-758 | Portal - Reports - Graphs by field staff competency | 6. Ready to go live | 2024-01-12 00:00:00 | 2023-10-31 11:18:37 | 2024-01-23 12:10:03
INRT-759 | API - Assets - Export assets to CSV | 4. Integration ready | 2024-01-12 00:00:00 | 2023-10-31 11:34:40 | 2024-01-24 17:04:10
INRT-760 | Portal - Assets - Export CSV | 3. In review | 2024-01-12 00:00:00 | 2023-10-31 11:35:13 | 2023-12-28 18:10:52
INRT-763 | App - Update readme file with all the instructions required for onboarding | 3. In review | 2024-01-12 00:00:00 | 2023-11-08 10:05:14 | 2023-12-28 18:14:08
INRT-767 | Project management - Planning/ Calls / Support - Release 4.8.0 | 1. Planned | 2024-01-12 00:00:00 | 2023-11-15 11:10:38 | 2024-01-29 08:41:19
INRT-778 | API - Resolve format issues and add the updated editor config file with code analysis rules | 4. Integration ready | 2024-01-12 00:00:00 | 2023-11-27 16:49:29 | 2024-01-11 11:35:08
INRT-779 | API - IR Teams Bot API changes/add-on APIs | 1. Planned | 2024-01-12 00:00:00 | 2023-11-28 12:25:01 | 2024-01-18 19:11:12
INRT-781 | API - Create new table for maintaining users involved for a incident. | 3. In review | 2024-01-12 00:00:00 | 2023-11-29 16:42:19 | 2023-12-28 18:13:18
INRT-785 | API - Accept image file type .HEIC in Create Notification, Incident Create APIs, Incident History. ( | 4. Integration ready | 2024-01-12 00:00:00 | 2023-12-05 14:38:40 | 2024-01-25 15:40:55
INRT-786 | Portal and App - Asset Geo Location - Set geo location of an asset and then the ability to update th | 2. Development /In Progress | 2024-01-12 00:00:00 | 2023-12-05 15:41:21 | 2024-01-08 03:32:27
INRT-790 | API - Asset Geo Location - Update asset APIs - Create/Update/Get/Get all to have Latitude, Longitude | 4. Integration ready | 2024-01-12 00:00:00 | 2023-12-13 11:07:47 | 2024-01-14 21:26:33
INRT-793 | UI - Add pages needed to support CRM Integrations | 2. Development /In Progress | 2024-01-12 00:00:00 | 2023-12-18 17:12:02 | 2024-01-08 02:58:53
INRT-794 | API - Integrate dropping message to dynamics integration service from create incident API. | 1. Planned | 2024-01-12 00:00:00 | 2023-12-18 17:14:47 | 2024-01-25 10:47:46
INRT-795 | API - Debug " Dynamics integration job ", a cron job to sync CRM case status & incident status | 3. In review | 2024-01-12 00:00:00 | 2023-12-18 17:16:32 | 2024-01-25 10:26:24
INRT-796 | API - Create QR code image for assets. Need to have app URL (get it from Raj) in the QR code data al | 3. In review | 2024-01-12 00:00:00 | 2023-12-18 17:27:28 | 2024-01-17 10:42:52
INRT-797 | App - When QR code pasted on the asset is scanned, it should take the user to report incident page w | 2. Development /In Progress | 2024-01-12 00:00:00 | 2023-12-18 18:24:26 | 2024-01-28 12:35:43
INRT-798 | Portal - Need changes in the request pay load sent for Update batches. | 4. Integration ready | 2024-01-12 00:00:00 | 2023-12-19 11:17:45 | 2024-01-21 16:02:42
INRT-799 | API - Need changes in the request pay load sent for Update batches and Create Batch | 3. In review | 2024-01-12 00:00:00 | 2023-12-19 11:27:00 | 2024-01-25 10:14:51
INRT-800 | Integrate AES encryption in IR app - Data transfer b/w client/server side | 3. In review | 2024-01-12 00:00:00 | 2023-12-19 16:25:24 | 2024-01-24 10:14:43
INRT-801 | Go through GDPR checklist, | 1. Planned | 2024-01-12 00:00:00 | 2023-12-19 16:27:52 | 2023-12-28 18:17:55
INRT-803 | Add “Unsubscribe me” feature to our outgoing emails by enabling it in the mailgun control Panel unde | 5. Testing | 2024-01-12 00:00:00 | 2023-12-20 16:52:14 | 2024-01-11 11:39:56
INRT-804 | Portal - Add Privacy policy link in the registration page (next to Terms & conditions link) | 1. Planned | 2024-01-12 00:00:00 | 2023-12-20 17:02:24 | 2024-01-19 09:52:13
INRT-808 | OQSHA - Figma design advance implementation | 2. Development /In Progress | 2024-01-12 00:00:00 | 2023-12-24 20:23:18 | 2024-01-16 12:15:11
INRT-810 | OQSHA: transform logo to gif with line animation | 2. Development /In Progress | 2024-01-12 00:00:00 | 2023-12-26 19:41:54 | 2023-12-30 00:32:37
INRT-811 | Portal - Develop landing page for OQSHA following the given theme | 3. In review | 2024-01-12 00:00:00 | 2023-12-28 12:52:30 | 2024-01-24 18:26:34
INRT-815 | OQSHA - Coordinate with Sandeep and Sheril to design landing screen | 2. Development /In Progress | 2024-01-12 00:00:00 | 2024-01-15 00:56:09 | 2024-01-15 01:02:54
INRT-817 | IR365 App KT call with Raj | 2. Development /In Progress | 2024-01-12 00:00:00 | 2024-01-22 01:45:15 | 2024-01-22 01:48:21
INRT-818 | Portal - OQSHA - Changes required in sidemenu | 2. Development /In Progress | 2024-01-12 00:00:00 | 2024-01-22 11:44:51 | 2024-01-29 08:11:45
INRT-820 | Testing - Go through project test cases, execute the test cases on IR Portal and App | 5. Testing | 2024-01-12 00:00:00 | 2024-01-23 17:12:32 | 2024-01-29 09:43:26
INRT-821 | OQSHA - Update the Registration Page as per shared Figma Design | 1. Planned | 2024-01-12 00:00:00 | 2024-01-23 17:18:29 | 2024-01-29 08:26:35
INRT-822 | OQSHA Portal - Update IR365 login page as per shared Figma design for OQSHA | 2. Development /In Progress | 2024-01-12 00:00:00 | 2024-01-23 17:41:15 | 2024-01-23 17:55:54
INRT-823 | Project setup and KT | 2. Development /In Progress | 2024-01-12 00:00:00 | 2024-01-23 20:43:38 | 2024-01-23 21:30:47
INRT-826 | UI : Notification Bugs | 2. Development /In Progress | 2024-01-12 00:00:00 | 2024-01-25 13:20:35 | 2024-01-28 12:29:29