## Sheet1
ID | Name | Priority | Project | Assigned to | Status | Due | Sprint | Budgeted | Billable | Non-billable | Code completion (%) | Created | Updated | Competency | Task owner
INRT-539 | Admin Portal - View single incident details | Medium | Incident Reporter 365 | Shivkant Dubey | Done | 2023-07-16 00:00:00 | Sprint 4.2.0 | 6 | 28.67 | 0.5 | 0 | 2023-06-27 08:18:00 | 2023-08-03 04:17:00 | Angular | Raj Kumar Pativada
INRT-576 | API - Any update on incident should be send as notification to the Assigned to User, Reported Incide | Medium | Incident Reporter 365 | Kumar Samarjeet | Done | 2023-08-08 00:00:00 | Sprint 4.2.0 | 9 | 20 | 2 | 100 | 2023-07-11 05:02:06 | 2023-08-07 09:31:02 | .NET | Sindhusha Balla
INRT-425 | API - Integrate having different config files for DEV/STG/PROD - Also make sure we have demo keys on | Medium | Incident Reporter 365 | Kumar Samarjeet | Stopped | 2023-06-21 00:00:00 | Sprint 4.2.0 | 2 | 2 | 0 | 100 | 2023-03-31 05:29:30 | 2023-07-20 12:18:55 | .NET | Sindhusha Balla
INRT-521 | API - Need a new user level setting says "show all incidents in feed" | Medium | Incident Reporter 365 | shreyansh J | Done | 2023-07-13 00:00:00 | Sprint 4.2.0 | 12 | 12.5 | 0 | 90 | 2023-06-23 05:35:39 | 2023-08-03 04:17:00 | .NET | Sindhusha Balla
INRT-560 | API - Need to improve New incident mail - Check with Raj what other details we need in there. | Medium | Incident Reporter 365 | Sindhusha Balla | Stopped | 2023-07-16 00:00:00 | Sprint 4.2.0 | 0 | 0 | 0 | 0 | 2023-06-30 08:38:42 | 2023-07-20 10:15:45 | .NET | Sindhusha Balla
INRT-97 | API - Send reminder emails to some of us when some org's subscription is about to expire | Medium | Incident Reporter 365 | Sanjana Yamawar | Done | 2023-08-02 00:00:00 | Sprint 4.2.0 | 6 | 34.68 | 0 | 0 | 2022-07-08 12:09:37 | 2023-08-03 04:17:00 | .NET | Raj Kumar Pativada
INRT-597 | API - Update authorization for Get incident API to be used for Admin Portal | Medium | Incident Reporter 365 | Bishal Mondal | Done | 2023-07-24 00:00:00 | Sprint 4.2.0 | 2 | 8.17 | 0 | 0 | 2023-07-24 09:10:41 | 2023-08-03 04:17:00 | .NET | Sindhusha Balla
INRT-540 | API - Update delete API to allow deletion of organisation owner instead of returning error. We shou | Medium | Incident Reporter 365 | Sanjana Yamawar | Done | 2023-06-30 00:00:00 | Sprint 4.2.0 | 9 | 9.83 | 0 | 0 | 2023-06-28 06:20:36 | 2023-08-03 04:17:00 | .NET | Sindhusha Balla
INRT-586 | API - Update delete notification API to do soft delete | Medium | Incident Reporter 365 | shreyansh J | Done | 2023-07-25 00:00:00 | Sprint 4.2.0 | 2 | 2 | 0.25 | 100 | 2023-07-20 08:57:44 | 2023-08-03 04:17:00 | .NET | Sindhusha Balla
INRT-604 | API - Update fieldstaff orgaisation API to fetch app user organisations whose showAllIncidents flag | Medium | Incident Reporter 365 | shreyansh J | Done | 2023-07-28 00:00:00 | Sprint 4.2.0 | 2 | 3.5 | 0 | 100 | 2023-07-28 14:17:31 | 2023-08-03 04:17:00 | .NET | Sindhusha Balla
INRT-575 | API - We need to have a new flag - allow site to all users - so that everytime a new user added to t | Medium | Incident Reporter 365 | shreyansh J | Done | 2023-07-16 00:00:00 | Sprint 4.2.0 | 10 | 10.17 | 0.58 | 100 | 2023-07-10 04:34:40 | 2023-08-03 04:17:00 | .NET | Sindhusha Balla
INRT-535 | App - Allow any user - App/fieldstaff/portal user to disconnect from App for an organisation - Error | Medium | Incident Reporter 365 | Abhilash Anand Katta | Done | 2023-07-16 00:00:00 | Sprint 4.2.0 | 2 | 11.5 | 0 | 0 | 2023-06-27 07:19:53 | 2023-08-06 15:56:28 | Angular | Sindhusha Balla
INRT-569 | Internal Team calls | Medium | Incident Reporter 365 | Sindhusha Balla | Done | 2023-07-16 00:00:00 | Sprint 4.2.0 | 50 | 11.72 | 0 | 100 | 2023-07-06 08:53:52 | 2023-08-20 20:22:40 |  | Sindhusha Balla
INRT-533 | POrtal & API - Integrate training module | Medium | Incident Reporter 365 | Raj Kumar Pativada | Stopped | 2023-07-16 00:00:00 | Sprint 4.2.0 | 0 | 6.77 | 0 | 0 | 2023-06-27 07:01:55 | 2023-07-17 10:08:08 | Angular | Sindhusha Balla
INRT-562 | Portal - Add information on all fields/flags which are not self explanatory. | Medium | Incident Reporter 365 | (Inactive) Tukka Gonda Domane | Done | 2023-07-16 00:00:00 | Sprint 4.2.0 | 6 | 26.75 | 1 | 0 | 2023-07-03 05:23:29 | 2023-08-03 04:17:00 | Angular | Sindhusha Balla
INRT-583 | Portal - New user level setting - Show all incidents in Feed also handle it accordingly in the app | Medium | Incident Reporter 365 | Sanjana Yamawar | Done | 2023-07-16 00:00:00 | Sprint 4.2.0 | 6 | 16.33 | 1 | 0 | 2023-07-17 10:12:06 | 2023-08-03 04:17:00 | Ionic | Raj Kumar Pativada
INRT-505 | Portal - Reports - Show number of incidents in each graph also enable it for Osmosys industry organi | Medium | Incident Reporter 365 | Shivkant Dubey | Done | 2023-06-02 00:00:00 | Sprint 4.2.0 | 6 | 31.17 | 2 | 0 | 2023-06-06 10:11:11 | 2023-08-03 04:17:00 | Angular | Raj Kumar Pativada
INRT-595 | Portal - Setup CI with gitlab and document the process such that all angular applications can follow | Medium | Incident Reporter 365 | Ashutosh Bisoyi | Development/In progress | 2023-07-16 00:00:00 | Sprint 4.2.0 | 16 | 33.25 | 1 | 0 | 2023-07-22 05:07:01 | 2023-08-27 18:37:10 | Angular | Raj Kumar Pativada
INRT-564 | Portal - We need to have a new flag - allow site to all users - so that everytime a new user added t | Medium | Incident Reporter 365 | Abhilash Anand Katta | Done | 2023-07-16 00:00:00 | Sprint 4.2.0 | 4 | 9 | 5.5 | 0 | 2023-07-04 08:39:20 | 2023-08-06 16:49:43 | Angular | Sindhusha Balla
INRT-589 | Portal : Update the label from Incident Updates to comments & have separate label for assigned t | Medium | Incident Reporter 365 | Shivkant Dubey | Done | 2023-07-27 00:00:00 | Sprint 4.2.0 | 2 | 26.83 | 3.25 | 100 | 2023-07-20 11:00:28 | 2023-08-20 19:27:24 | Angular | Sindhusha Balla
INRT-561 | Project management & Support - v4.2.0 | Medium | Incident Reporter 365 | Sindhusha Balla | Done | 2023-07-30 00:00:00 | Sprint 4.2.0 | 100 | 109.5 | 0 | 0 | 2023-07-03 03:14:25 | 2023-08-03 04:17:00 | .NET | Sindhusha Balla
INRT-619 | Release 4.2 - Deployment | Medium | Incident Reporter 365 | Raj Kumar Pativada | Development/In progress | 2023-08-15 00:00:00 | Sprint 4.2.0 | 8 | 5.5 | 0 | 0 | 2023-08-07 03:43:19 | 2023-08-07 03:49:43 | Angular | Raj Kumar Pativada
INRT-584 | Testing - Go through Portal/Admin Portal/App for IR - Understand features available | Medium | Incident Reporter 365 | Suryakanta Sahoo | Done | 2023-07-20 00:00:00 | Sprint 4.2.0 | 16 | 17 | 0 | 100 | 2023-07-19 05:20:17 | 2023-08-03 04:17:00 |  | Sindhusha Balla
INRT-577 | Testing - IR KT from Sanjana | Medium | Incident Reporter 365 | (Inactive) RAMYASRI TOOTICHERLA | Done | 2023-07-11 00:00:00 | Sprint 4.2.0 | 20 | 13.5 | 0 | 100 | 2023-07-11 11:16:05 | 2023-08-03 04:17:00 |  | Sindhusha Balla
INRT-570 | Testing - KT on IR & VOC. Go through IR 4.2 sprint tasks & Create test plan | Medium | Incident Reporter 365 | Lakshmana Rao | Done | 2023-07-16 00:00:00 | Sprint 4.2.0 | 27 | 17.5 | 0 | 0 | 2023-07-06 12:19:48 | 2023-08-03 04:17:00 |  | Sindhusha Balla
INRT-601 | Testing - Test & Create bugs on 4.2 tasks | Medium | Incident Reporter 365 | Sanjana Yamawar | Done | 2023-07-27 00:00:00 | Sprint 4.2.0 | 16 | 54 | 0 | 0 | 2023-07-27 05:37:54 | 2023-08-06 13:53:17 |  | Sindhusha Balla
INRT-578 | Testing : Go through IR 4.2 sprint plan - https://osmosysasia-my.sharepoint.com/:x:/g/personal/rajku | Medium | Incident Reporter 365 | Sanjana Yamawar | Done | 2023-07-13 00:00:00 | Sprint 4.2.0 | 1 | 1 | 0 | 100 | 2023-07-12 09:51:05 | 2023-08-03 04:17:00 |  | Sindhusha Balla
INRT-579 | Testing: Go through testing docs listed & setup the GITLAB repos for the projects that you are p | Medium | Incident Reporter 365 | Sai prashanth Kona | Done | 2023-07-12 00:00:00 | Sprint 4.2.0 | 24 | 6.75 | 0 | 0 | 2023-07-12 09:54:04 | 2023-08-03 04:17:00 |  | Sindhusha Balla
INRT-582 | Web Portal and app revamping | Medium | Incident Reporter 365 | Anand Prakash | Stopped | 2023-07-16 00:00:00 | Sprint 4.2.0 | 40 | 0.33 | 0 | 0 | 2023-07-17 02:33:25 | 2023-07-22 08:34:12 | UI/UX | Anand Prakash