## Sheet1
Project | Task name | Assigned to | Comments | Actual comment date | Commented date | Billable | Non-billable | Code completion (%) | Billing status | Task status | Competency | Commented by
OQSHA | (Action Tracker - Buttons) Portal - Action tracker should have buttons for status changing similar t | Rupam | Tested the flow with all the cases. Verified its working, same as safety alerts. Development completed 100%. | 2025-08-23 17:11:17 | 2025-08-23 17:11:17 | 1 | 0 | 100 | Testing | 6. Ready to go live | Angular | Rupam
OQSHA | (Action Tracker - Buttons) Portal - Action tracker should have buttons for status changing similar t | Rupam | https://gitlab.osmosys.co/incident-reporter/incident-reporter-angular-portal/-/merge_requests/3947 Assigning for review Development completed 100%. | 2025-08-23 13:53:53 | 2025-08-23 13:53:53 | 0 | 0 | 100 | Miscellaneous | 6. Ready to go live | Angular | Rupam
OQSHA | (TTK UAT) Portal - Action tracker - New status "Site EHS Release" | Rupam | Updating status to waiting dependency since API task is not done. Will test once its done, no changes required from UI side. Development completed 70%. | 2025-08-23 13:54:44 | 2025-08-23 13:54:44 | 0 | 0 | 70 | Miscellaneous | 6. Ready to go live | Angular | Rupam
OQSHA | (Action Tracker - Buttons) Portal - Action tracker should have buttons for status changing similar t | Rupam | Added status buttons based on flag. Updated status on based of filled fields and added conditions to disable buttons based on role. Development completed 70%. | 2025-08-23 06:08:42 | 2025-08-23 06:08:42 | 0 | 0 | 70 | Coding | 6. Ready to go live | Angular | Rupam
OQSHA | (Action Tracker - Buttons) Portal - Action tracker should have buttons for status changing similar t | Rupam | Completed implementation to enable or disable buttons based on logged in user role. Development completed 100%. | 2025-08-23 17:10:27 | 2025-08-23 17:10:27 | 3 | 0 | 100 | Coding | 6. Ready to go live | Angular | Rupam
OQSHA | (TTK UAT) Portal - Action tracker - New status "Site EHS Release" | Rupam | *Comments for Non-billable hours* If due date, assigned to, priority are filled - Individual tasks are created & tasks are directly assigned to respective persons in "Assigned" status. If due date, assigned to, priority fields are NOT filled - parent record should stay as it is & it should be assigned to "Site EHS" by default & in "Open" status. Site EHS will open the record, fill the pending details and submit - that's when the individual tasks are created & assigned to individuals in "Assigned" status. Implemented this but then got to know it will be handled from backend Development completed 70%. | 2025-08-23 17:12:55 | 2025-08-23 17:12:55 | 0 | 1 | 70 | Coding | 6. Ready to go live | Angular | Rupam
OQSHA | (Action Tracker - Buttons) Portal - Action tracker should have buttons for status changing similar t | Rupam | Replied. Assigning back. https://gitlab.osmosys.co/incident-reporter/incident-reporter-angular-portal/-/merge_requests/3947 Development completed 100%. | 2025-08-23 19:24:32 | 2025-08-23 19:24:32 | 0.5 | 0 | 100 | Coding | 6. Ready to go live | Angular | Rupam